## Blad1
Date | Activities Mark | Activities Jeroen | Notes
2019-03-09 | Project plan | Project plan
2019-04-09 | Project plan + Research 3D Vision | Project plan + Research 3D Vision | Morfologisch overzicht opgesteld
2019-10-09 | Research 3D Vision + installing Ubuntu 18 | Research 3D Vision + installing Ubuntu 18 | Moeite met het opstellen van kesselringmethode afhankelijk van morfologisch overzicht, afspraak met Ruud inplannen
2019-11-09 | Installing ROS + C++ tutorial | Installing ROS + C++ tutorial | Afspraak met Ruud over werkwijze planning software. Conclusie geen gebruik maken van kesselring, maar kijken naar mogelijkheden in library en deze uitwerken
9-17-2019 | Started setting up pipeline with RealSense SDK | Finding TF with PCL | Problemen bij koppelen van library aan C++ code
9-18-2019 | Pipeline for camera + getting point cloud from depth data | Visualization data stream + research segmentation | Gevonden dat huidige camera slecht zwarte objecten kan zien. Mogelijke oplossing RealSense D400 serie met stereo camera
2019-09-20 |  | made PLY to PCD converter
2019-09-24 | Point cloud to PCD + started with filtering the point cloud | Research segmentation | Na een gesprek met pablo gekozen om bij de huidige camera te blijven. Disclaimer toevoegen aan het project waarin we aangeven dat zwarte objecten niet gedetecteerd kunnen worden met de camera die we nu gebruiken
2019-09-25 | Started GitHub Repo + made Voxel Grid Filter + made Pass Through filter | Fixed visualization example file + integrated visualization in segmentation files
2019-09-29 |  | visualization implemented in segmentation
2019-10-01 | Pipeline setup + 2D ROI in point cloud research | Started making Main.cpp | Pipeline code was overwritten so we had to make it again
2019-10-02 | Object detection with ROI | Main.cpp fixed pipeline, started visualization and class diagram
2019-10-06 | Fixed object detection with ROI
2019-10-07 |  | Main.cpp fixed visualization and updated class diagram
2019-10-08 | Started with YOLO | Main.cpp fixed tf and started segmentation | Don’t remove python 3.6 from ubuntu!
2019-10-09 | Setting up YOLO | Worked on implementing segmentation
2019-11-05 | Little fixes on filters and continued in YOLO | Fixed table segmentation | Removing 0 0 0 points improves TF
2019-11-06 | continued YOLO | Fixed object segmentation and added PCD filters and cleaned up code | Due to the quality of the PCD it determines the quality of the TF. Bad PCD’ s make the TF twist
2019-11-07