## Blad1
Date | Activities Mark | Activities Jeroen | Notes
2019-03-09 | Project plan | Project plan
2019-04-09 | Project plan + Research 3D Vision | Project plan + Research 3D Vision | Morfologisch overzicht opgesteld
2019-10-09 | Research 3D Vision + installing Ubuntu 18 | Research 3D Vision + installing Ubuntu 18 | Moeite met het opstellen van kesselringmethode afhankelijk van morfologisch overzicht, afspraak met Ruud inplannen
2019-11-09 | Installing ROS + C++ tutorial | Installing ROS + C++ tutorial | Afspraak met Ruud over werkwijze planning software. Conclusie geen gebruik maken van kesselring, maar kijken naar mogelijkheden in library en deze uitwerken
9-17-2019 | Started setting up pipeline with RealSense SDK | Finding TF with PCL | Problemen bij koppelen van library aan C++ code
9-18-2019 | Pipeline for camera + getting point cloud from depth data | Visualization data stream + research segmentation | Gevonden dat huidige camera slecht zwarte objecten kan zien. Mogelijke oplossing RealSense D400 serie met stereo camera
2019-09-20 |  | made PLY to PCD converter
2019-09-24 | Point cloud to PCD + started with filtering the point cloud | Research segmentation | Na een gesprek met pablo gekozen om bij de huidige camera te blijven. Disclaimer toevoegen aan het project waarin we aangeven dat zwarte objecten niet gedetecteerd kunnen worden met de camera die we nu gebruiken
2019-09-25 | Started GitHub Repo + made Voxel Grid Filter + made Pass Through filter | Fixed visualization example file + integrated visualization in segmentation files
2019-09-29 |  | visualization implemented in segmentation
2019-10-01 | Pipeline setup + 2D ROI in point cloud research | Started making Main.cpp | Pipeline code was overwritten so we had to make it again
2019-10-02 | Object detection with ROI | Main.cpp fixed pipeline, started visualization and class diagram
2019-10-06 | Fixed object detection with ROI
2019-10-07 |  | Main.cpp fixed visualization and updated class diagram
2019-10-08 | Started with YOLO | Main.cpp fixed tf and started segmentation | Don’t remove python 3.6 from ubuntu!
2019-10-09 | Setting up YOLO | Worked on implementing segmentation
2019-11-05 | Little fixes on filters and continued in YOLO | Fixed table segmentation | Removing 0 0 0 points improves TF
2019-11-06 | continued YOLO | Fixed object segmentation and added PCD filters and cleaned up code | Due to the quality of the PCD it determines the quality of the TF. Bad PCD’ s make the TF twist
2019-11-07 | Fixed YOLO with objects | Updated class diagram and added get TF class | made new pictures of the objects from different heights
2019-11-08 | Finished ROS tutorial | Reinstalled laptop
2019-11-12 | Version management ROS with Realsense SDK | Cleaned up code, added system time check, updated research doc | Realsense-ROS version 2.2.9 ¦ Realsense SDK version 2.29.0
2019-11-13 | Fixed ROS with Realsense SDK, started ROS research | Finished getTF, updated class diagram
2019-11-19 | Started ROS with yolo | TF calculation | We might not need Realsense-ROS because the pipeline is already up and running
2019-11-20 | continued with ROS yolo | TF broadcaster
2019-11-26 | Integrated pipeline into main and started with code for testing | Started with ROS yolo and fixed client server | Jeroen took ROS yolo over
2019-11-27 | Fixed calculation of the angle of an object and finished code for testing | continued ROS yolo | test data is saved in .csv file that is in the build folder
2019-11-29 | Integrated pipeline into ROS | Fixed client service with images
2019-12-02 | Started testplan | Integrated client service into main
2019-12-03 | Continued with testplan | Working on integration yolo | cv_bridge doesn’ t work with python3, yolo only works with python3. We chose to use a communication protocol made by Merian
2019-12-04